## Attendees
Silicon Valley Event — Attendees
The Stanford Park Hotel ¦ Mon 4 May → Thu 7 May ¦ ~57 attendees
# | Name | Function | Role / Notes | Hands-on Group | Tech Lead? | Hands-on Groups | COUNT
Exec Team | [5 empty] | 1. Executive Board / Management | 5
1 | Darren Roos | Exec Team |  | 1. Executive Board / Management |  | 2. Sales -- targeting and account management | 5
2 | Mark Moffat | Exec Team |  | 1. Executive Board / Management |  | 3. Pre-Sales -- technical demo'ing | 5
3 | Fred Brady | Exec Team |  | 1. Executive Board / Management |  | 4. R&D | 4
Core Sales | [5 empty] | 5. Customer Support & Success | 4
4 | Simon Niesler | Core Sales |  | 2. Sales -- targeting and account management |  | 6. AI Product Unit | 5
5 | Ann Marie Mullally | Core Sales |  | 2. Sales -- targeting and account management |  | 7. Marketing | 5
6 | Goiuri Hernández | Core Sales |  | 10. IT |  | 8. HR | 5
7 | Justin Bigger | Core Sales |  | 12. Sales -- targeting and accountmanagement - Team B | Yes | 9. Finance | 5
8 | James Greaves | Core Sales |  | 3. Pre-Sales -- technical demo'ing |  | 10. IT | 5
9 | James Thompson | Core Sales |  | 2. Sales -- targeting and account management |  | 11. M&A | 5
10 | Andre Robberts | Core Sales |  | 2. Sales -- targeting and account management |  | 12. Sales -- targeting and accountmanagement - Team B | 4
11 | Mattias Bolander | Core Sales |  | 12. Sales -- targeting and accountmanagement - Team B
12 | Mathieu Daudigny | Core Sales |  | 3. Pre-Sales -- technical demo'ing
13 | Stephanie Poore | Core Sales |  | 3. Pre-Sales -- technical demo'ing
14 | Matt Breslin | Core Sales |  | 8. HR
15 | Hannes Liebe | Core Sales |  | 9. Finance
16 | Mark Buongiorno | Core Sales |  | 12. Sales -- targeting and accountmanagement - Team B
17 | Herman Niewoudt | Core Sales |  | 12. Sales -- targeting and accountmanagement - Team B
18 | Travis Johnstone | Core Sales |  | 3. Pre-Sales -- technical demo'ing
Core Product / GCS
19 | Cathie Hall | Core Product / GCS |  | 4. R&D
20 | Mairi Campbell | Core Product / GCS |  | 4. R&D
21 | Dan Dutton | Core Product / GCS |  | 4. R&D | Yes
22 | Raymond Jones | Core Product / GCS |  | 5. Customer Support & Success
23 | Vaibs Kumar | Core Product / GCS |  | 7. Marketing | Yes
24 | Tony Johnson | Core Product / GCS |  | 5. Customer Support & Success
25 | Bob De Caux | Core Product / GCS |  | 5. Customer Support & Success | Yes
AI BU
26 | Somya Kapoor | AI BU |  | 10. IT
27 | Jonathan Hyden | AI BU |  | 3. Pre-Sales -- technical demo'ing | Yes
28 | Ravi Bulusu | AI BU |  | 2. Sales -- targeting and account management | Yes
29 | Elvis Pinjagic | AI BU |  | 7. Marketing
30 | Kriti Sharma | AI BU |  | 8. HR | Yes
31 | Kurt Kemmerly | AI BU |  | 5. Customer Support & Success
32 | Nick Vandivere | AI BU |  | 11. M&A | Yes
33 | Jon Zorio | AI BU |  | 6. AI Product Unit
34 | Matt Kempson | AI BU |  | 6. AI Product Unit
35 | Matt Quinn | AI BU |  | 6. AI Product Unit
36 | Bisher Deirki | AI BU |  | 6. AI Product Unit
37 | Adi Kumar | AI BU |  | 1. Executive Board / Management | Yes
38 | Matt Ely | AI BU |  | 6. AI Product Unit | Yes
Marketing
39 | Oliver Pilgerstorfer | Marketing |  | 7. Marketing
40 | Andreas Georgiou | Marketing |  | 7. Marketing
41 | Sara Hill | Marketing |  | 7. Marketing
HR
42 | Mihita Podobnik | HR |  | 8. HR
43 | Laura Bennett | HR |  | 8. HR
Other / Strategy
44 | Joe Dormani | Other / Strategy |  | 1. Executive Board / Management
45 | Christian Pedersen | Other / Strategy |  | 8. HR
M&A
46 | Lance Olmsted | M&A |  | 11. M&A
47 | Tim Forkner | M&A |  | 11. M&A
48 | Danilo Prates | M&A |  | 9. Finance | Yes
49 | Jim Hoefflin | M&A |  | 11. M&A
50 | Antoine Bisson | M&A |  | 4. R&D
51 | Rob Hortopp | M&A |  | 11. M&A
50 | Gregory Briedenbach | attendinig in place of Antoine Bisson
IT
52 | Robi Gone | IT |  | 10. IT
53 | Jorge García Díaz | IT |  | 10. IT | Yes
54 | Mubashir Nisar | IT |  | 10. IT
Finance
55 | Matthias Heiden | Finance |  | 9. Finance
56 | Jordan Setterfield | Finance |  | 9. Finance
57 | Jonathan Park | Finance |  | 9. Finance
TOTAL ATTENDEES
57

## Group Membership
1. Executive Board / Management |  |  | 2. Sales -- targeting and account management |  |  | 3. Pre-Sales -- technical demo'ing |  |  | 4. R&D
Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead?
Adi Kumar | AI BU | Yes | Andre Robberts | Core Sales |  | James Greaves | Core Sales |  | Antoine Bisson
Darren Roos | Exec Team |  | Ann Marie Mullally | Core Sales |  | Jonathan Hyden | AI BU | Yes | Dan Dutton | Core Product / GCS | Yes
Mark Moffat | Exec Team |  | James Thompson | Core Sales |  | Mathieu Daudigny | Core Sales |  | Mairi Campbell | Core Product / GCS
Fred Brady | Exec Team |  | Ravi Bulusu | AI BU | Yes | Stephanie Poore | Core Sales |  | Cathie Hall | Core Product / GCS
Joe Dormani | Other / Strategy |  | Simon Niesler | Core Sales |  | Travis Johnstone | Core Sales |  | Gregory Briedenbach | Core Product / GCS
5. Customer Support & Success |  |  | 6. AI Product Unit |  |  | 7. Marketing |  |  | 8. HR
Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead?
Bob De Caux | Core Product / GCS | Yes | Bisher Deirki | AI BU |  | Andreas Georgiou | Marketing |  | Christian Pedersen | Other / Strategy
Kurt Kemmerly | AI BU |  | Jon Zorio | AI BU |  | Elvis Pinjagic | AI BU |  | Kriti Sharma | AI BU | Yes
Raymond Jones | Core Product / GCS |  | Matt Ely | AI BU | Yes | Oliver Pilgerstorfer | Marketing |  | Laura Bennett | HR
Tony Johnson | Core Product / GCS |  | Matt Kempson | AI BU |  | Sara Hill | Marketing |  | Matt Breslin | Core Sales
|  |  | Matt Quinn | AI BU |  | Vaibs Kumar | Core Product / GCS | Yes | Mihita Podobnik | HR
9. Finance |  |  | 10. IT |  |  | 11. M&A |  |  | 12. Sales -- targeting and accountmanagement - Team B
Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead? | Name | Function | Tech Lead?
Danilo Prates | M&A | Yes | Goiuri Hernández | Core Sales |  | Jim Hoefflin | M&A |  | Herman Niewoudt | Core Sales
Hannes Liebe | Core Sales |  | Jorge García Díaz | IT | Yes | Lance Olmsted | M&A |  | Justin Bigger | Core Sales | Yes
Jonathan Park | Finance |  | Mubashir Nisar | IT |  | Nick Vandivere | AI BU | Yes | Mark Buongiorno | Core Sales
Jordan Setterfield | Finance |  | Robi Gone | IT |  | Rob Hortopp | M&A |  | Mattias Bolander | Core Sales
Matthias Heiden | Finance |  | Somya Kapoor | AI BU |  | Tim Forkner | M&A

## Agenda
Silicon Valley Event — Agenda
The Stanford Park Hotel ¦ Monday 4 May → Thursday 7 May ¦ May 2026
Time | Session | Speakers / Content | Format | Location | Notes
DAY 1 — MONDAY 4 MAY ¦ "Arrival & Opening Dinner"
Afternoon | Arrivals — check in to hotel |  | — | The Stanford Park Hotel | Transfers from SFO/SJC if needed
18:00 – 18:30 | Opening note | Mark/Darren | Scene Setting | Hotel Room xx | Cursor CEO (Michael Truell) also being explored for Monday dinner |  | Day 2 All about hands on - 2 technologies
18:30 – 19:30 | Founder Spotlight / Vaibs/Adi/Nick Orchestrated | TBD (OpenAI, Nvidia) | 10 minute Founding stories - inspirational | Hotel Room xx |  |  | Day 3 - What is IFS doing about this.
19:30 – 21:30 | Opening Dinner. -- Instructions to be hands on with replit - come in warmed up for next morning | Vaibs/Nick/Adi - on Getting any logistics or practicalieis like downloads/last pre reads etc | Social / Networking | Hotel Room xx | Seated dinner, informal networking |  | Hands on build groups and cohorts - lets make them logical
this plays as pre work for the following day
DAY 2 — TUESDAY 5 MAY ¦ "Show the Team What's Possible" | [5 empty] | Museum | Room Config = Round tables
07:30 – 09:00 | Explore Working Breakfast | 2-3 Startup founders | Mingle and Breakfast | Hotel |  |  | Learning Lab room - Kate to confirm
09:00 – 09:30 | Transfer to Computer History Museum | n/a | n/a | Computer History Museum | IFS Organised transport - do not book taxis
09:30 –10:00 | Opening Inspirational Keynote | Mark Moffat - Hand-off Vaibs/Nick | Keynote | Learning Lab | What to expect today, how the hands-on works
10:00 – 10:45 | Opening Keynote (Technical) | Chamath / Ali / Anthropic Senior / NVIDIA | Keynote | Learning Lab | TBC
10:45 – 11:00 | Comfort Break
11:00 – 13:00 | Hands-on Block 1 — Replit (vibe coding) | TBC - Replit / Loveable | Hand-on Keyboard | Learning Lab | External Rep guiging through the session | Vendors in learning lab should only be the ones representing the tools
13:00 – 13:45 | Lunch
13:45 – 16:00 | Hands-on Block 2 - Anthropic | Breakout teams using Claude COwork to build Skills and agents and automation | Hand-on Keyboard | Learning Lab | Claude Cowork | 1/2 vendor tech
16:00 – 16:30 | Buffer - but build in comfort break for hands on block 2
1630 - 17:00 | Transfer back to hotel |  |  |  |  | Show 1 or 2 multiple tech for art of the possible
1845 - 1915 | Transfer to Restaurant |  |  | Name of Restaurant
19:15 - 20:00 | Dinner and Mixer | 2-3 Punctuate with Startup founders |  | Name of Restaurant
DAY 3 — WEDNESDAY 6 MAY ¦ "Present, Learn & Plan" --> How do we tranform IFS to AI Native --> Exercise + Play Back -- North Start KPIs of the new order
07:30 – 09:00 | Check Working breakfast |  | — | Hotel |  | GOldman confirmed - risks from saas market - Opening on Day 3
09:00 – 10:00 | Goldman Market risks SaaS |  | Keynote | Hotel room xx
10:00 - 11:00 | KPIs of the new world Session | Functional groups |  | Hotel room xx | Per function Vs Group Level
11;00 - 12:00 | Working session — 'What does your function look like on 1 Jan 2027?' |  |  |  |  | COuld be between 1700 and 1900 on tuesday - this would be the vendors that we can get
12:00 - 13:00 | Lunch |  | Social | Hotel |  | Clay/Apollo/8090
13:00 – 14:00 | Working session — 'What does your function look like on 1 Jan 2027?' | Functional groups
14:00-15:30 | Product Launch Strategy in an AI-native world | Andreas Georgiou / Nick --> Adi to chase
15:00-15:30 | Break
15:30 – 16:30 | Playback of the working sessions? | TBD |  | Main Room |  |  | Goal - proper engagement - FOunder Attendance engagement
16:30 – 17:00 | Closing Remarks & What's Next | Mark Moffat / Darren Roos | Keynote | Main Room | Concrete next steps, ownership, timelines |  | Founders mix for drinks and dinner
19:00 – 21:30 | Closing Dinner |  | Social | Hotel Restaurant
Expo type dynamic -
DAY 4 — THURSDAY 7 MAY ¦ Departures / Free Morning
07:00 – 09:00 | Breakfast & Checkout |  | — | Hotel |  |  | Either day 2 evening flexibility
Morning | Free morning — optional 1:1s / small groups | Self-organised | Informal | Hotel Lobby / Café | For those with later flights |  | start of Day 3
09:00+ | Departures |  | — | Hotel / Airport | Transfers to SFO/SJC as needed
Maybe founders on both morning - if we can logisticall arrange for that.
13:30 – 15:30 | Optional Factory visit on Day 4 | TBD | Visit / Talks | Offsite — 1x factory | 1x factory visit
Factory visit - make it optional for Day 4
Cursor, Replit, Tessl, Traycer, 8090.ai ¦¦ Sales: Clay, Apollo.io, 11x.ai ¦¦ Marketing: 6sense, Demandbase, Mutiny ¦¦ IT/HR/Fin: Aisera, Glean

## Speaker Tracker
Speaker & Company Tracker
Outreach status for Silicon Valley Event
Company | Contact / Speaker | Category | Who's Reaching Out | Intro Via | Status | Confirmed? | Notes
High-profile / Keynote
Databricks | Ali Ghodsi (CEO) | Keynote | Mark Moffat | Mark's contact | To reach out | No
Andrew Ng | Andrew Ng | Keynote | Nick Vandivere | Nick's contact | To reach out | No
Goldman Sachs | Joe Porter | Keynote | Mark Moffat | Eva prepping email | Draft email | No | New unit economics for software
Anthropic | TBC | Labs | Vaibs/Glen |  | Pending | No
OpenAI | TBC | Labs | John P (Hg) | Hg checking | Pending | No | Monday evening speaker
Nvidia | TBC | Keynote |  |  | To reach out | No | Monday evening — alongside OpenAI
Function-specific — Sales
Clay | TBC | Sales | John P (Hg) x Vaibs | Hg checking | Pending | No | Also in initial outreach list
Apollo.io | TBC | Sales | John P (Hg) x Vaibs | Hg checking | Pending | No
11x.ai | TBC | Sales | John P (Hg) x Vaibs | Hg checking | Pending | No
Function-specific — Marketing
6sense | TBC | Marketing | John P (Hg) | Hg checking | Pending | No
Demandbase | TBC | Marketing | John P (Hg) | Hg checking | Pending | No
Mutiny | TBC | Marketing | John P (Hg) | Hg checking | Pending | No
Function-specific — IT / HR / Finance
Aisera | TBC | IT/HR/Finance | John P (Hg) | Hg checking | Pending | No
Glean | TBC | IT/HR/Finance | John P (Hg) | Hg checking | Pending | No | Also in initial outreach list
Tools / Dev Platforms
Cursor | Michael Truell (CEO) | Tools | Vaibs Kumar | Direct email | Emailed | No | Vaibs has emailed CEO. Also exploring for Monday dinner.
Replit | TBC | Tools |  |  | To reach out | No
Tessl | TBC | Tools | John P (Hg) | Hg intro | Pending | No | John P checking
Traycer | TBC | Tools | Vaibs Kumar | Hg intro | Pending | No | John P checking
8090.ai | TBC | Tools | Mark Moffat |  | To reach out | No
Wednesday External Visit
1x | TBC | Factory Visit | TBC |  | To reach out | No | Wednesday 13:30–15:30 factory visit

## Hands-on Exercises
Hands-on Exercise Planning
Single hands-on day (Tuesday), groups of 5 with tech leads
Exercise | Description | Tool(s) | Duration | Day / Slot | Owner | Notes
Exercise: Build an App | Use Replit (or Tessl/Traycer) to build an app in breakout teams. Vaibs to confirm which app. | Replit / Tessl / Traycer | ~6.5 hours (11:00–17:30) | Tuesday | TBC | Single extended hands-on block with lunch break.
Presentations of Apps Built | Teams present the apps they built on Tuesday. Each group demos their work. | N/A — presentation | ~4 hours (08:30–12:30) | Wednesday | TBC | Wed afternoon: external visit (1x factory) + Product Launch Strategy.
EXERCISE IDEAS — Build an App (Tuesday, Replit / Tessl / Traycer)
Function | Exercise Name | What They Build | Skills Learned | Output | Difficulty | Notes
Sales | AI Deal Room | Account intelligence briefs from a company name | Web research + data synthesis + doc gen | Working skill + sample brief | Medium | Directly useful for sales
Marketing | Campaign Generator | Brief → blog post, LinkedIn posts, email sequence, event flyer | Brand encoding + multi-format content gen | Complete campaign pack | Medium | Replaces a content team's sprint
Finance | Expense Intelligence | Receipt photos → extract → categorise → rename → summary | Image analysis + business rules + structured output | Working expense processor | Medium | Live demo with real receipts
IT | Incident Response Agent | Alert/error log → root cause diagnosis, remediation runbook | Technical reasoning + operational docs | Diagnostic agent + playbook | Medium-High | Great for IT and Product
HR | Onboarding Orchestrator | Name/role/dept → welcome email, schedule, access list, training | Org knowledge encoding + doc gen | Complete new hire pack | Medium | Applicable across all functions
GROUP ASSIGNMENTS — 11 groups of 5
Group # | Tech Lead | Member 1 | Member 2 | Member 3 | Member 4 | Mix (Technical / Non-technical)
Group 1
Group 2
Group 3
Group 4
Group 5
Group 6
Group 7
Group 8
Group 9
Group 10
Group 11
LOGISTICS CHECKLIST
Item | Description | Owner | Status | Deadline | Priority | Notes
Claude Licenses | Ensure Claude access for all 57 attendees | TBC | Not started | TBC | High | Check Anthropic team pricing
Local Admin | Local admin rights on all machines | IT (Robi / Jorge) | Not started | TBC | High
Tool Decision | Decide between Replit, Tessl, Traycer | Vaibs Kumar | In discussion | TBC | High
App Idea | Define the app(s) to build | Vaibs / Nick / Adi | Not started | TBC | Medium | Needs to work across functions
Wi-Fi / AV | Confirm venue Wi-Fi (57 concurrent), screens, mics, power | Eva / Venue | Not started | TBC | High
Exercise Materials | Prep guides, prompts, starter templates | Tech Leads | Not started | TBC | Medium
Group Assignments | Assign attendees to 11 groups with tech leads | Vaibs / Nick / Adi | Not started | TBC | Medium | Balance technical / non-technical
Venue Booking | Confirm Stanford Park Hotel dates, breakout rooms, catering | Eva | Not started | TBC | High | Need main room + breakout spaces
Hotel Block | Reserve rooms at Stanford Park Hotel | Eva / Kate | Not started | TBC | High
Dinner Venues | Book Mon, Tue, Wed dinners | Eva | Not started | TBC | Medium | Three different restaurants?
Airport Transfers | Arrange SFO/SJC transfers | Kate | Not started | TBC | Medium | Collect flight details from attendees

## Exercise Ideas
Silicon Valley Event — Hands-On Exercise Design Ideas
Brainstorm as of 4 April 2026 — to be refined with Vaibs, Nick & Adi
EXERCISE STRATEGY: DEMO vs HANDS-ON
Element | Description | Skill / Tool | Audience | Duration | Notes
LIVE DEMO: Expense Automation | Adi demos the full expense pipeline live — the 'holy shit' moment. | sort-my-expenses pipeline | Full room | 15 min | Skip osxphotos — use pre-staged receipts. Playwright drives IFS Cloud live.
HANDS-ON: Create a Deck | Everyone gives Claude a brief → polished 15-slide deck back. | pptx skill | All functions | 15–20 min | Gateway drug. Everyone makes decks.
HANDS-ON: Generate a PRD | Product idea → full engineering-ready spec. | adi-prd-generator skill | Product / GCS / AI BU | 20–30 min | Best for technical or product-minded attendees.
HANDS-ON: Build a Prototype | Non-technical people build a clickable HTML prototype. The 'walls coming down' moment. | html-prototype-builder skill | Sales / Marketing / M&A / Finance | 30 min | Non-coders building something real.
HANDS-ON: Co-Author a Document | Co-write a real document with Claude in 15 min. | docx + doc-coauthoring skill | Finance / HR / M&A | 15–20 min | Tangible, practical, immediately applicable.
META: Build a Skill | Teach Claude a reusable workflow. 'Tool' vs 'colleague'. | skill-creator skill | Tech leads / advanced | 30–45 min | Claude doesn't just do tasks, it learns workflows.
EXPENSE DEMO: SIMPLIFIED PIPELINE
Step | What Happens | Skill / MCP Used | Setup Required | Complexity | Demo Impact
1. Stage receipts | Pre-load folder with 8–10 receipts | Manual prep | Folder with sample receipts |  | Sets the scene
2. Categorise & rename | Claude reads each receipt, extracts details, renames | categorise-expense skill | Skill installed in Cowork | Low | HIGH — real-time magic
3. File into IFS Cloud | Playwright drives browser: creates expense sheet, adds items, uploads | file-expenses-thor + Playwright MCP | Playwright + IFS Cloud access | Medium | VERY HIGH — showstopper
EXERCISE MENU BY FUNCTION
Function | Primary Exercise | Secondary Exercise | Skill(s) | Group Size | Notes
Sales (4 groups) | Build competitive battlecard | Prototype a deal room app | sales:competitive-intelligence, html-prototype-builder | ~5 per group | 20 sales people = 4 groups
Marketing (1 group) | Generate campaign deck from brief | Build landing page prototype | pptx, html-prototype-builder | ~5 | Visual output = immediate satisfaction
Product / GCS (1–2) | Generate PRD from rough idea | Build clickable prototype from PRD | adi-prd-generator, html-prototype-builder | ~5 | Chain PRD → prototype
AI BU (2 groups) | Build a skill or automate workflow | Meta: create reusable skill | skill-creator | ~5 | Most technical — push them further
Finance (1 group) | Co-author financial analysis doc | Build budget model from brief | docx, xlsx | ~5 | Practical output to take home
HR (1 group) | Draft org design proposal | Automate onboarding checklist | docx, doc-coauthoring | ~3–5 | 'AI replaces process, not people'
IT (1 group) | Prototype internal tool | Automate support workflow | html-prototype-builder, skill-creator | ~5 | Build something users would want
M&A (1 group) | Target company research brief | Due diligence checklist | sales:account-research, docx | ~5 | Research-heavy use case

## Decisions to be made
Decisions to be made — Agenda & Logistics
# | Topic | Decision Needed | Owner | Notes / Context
1 | Day 2 technical opener | Who speaks? Chamath (1890) vs Ali (Databricks) vs Anthropic senior vs Nvidia. Need 1 confirmed. | Mark Moffat | Must bring technical/market colour to open the hands-on day. Mark has written to Chamath.
2 | Anthropic partnership & moderators | Can we get 4–5 Anthropic people in the room as Claude moderators on Day 2 afternoon? Tied to renegotiating the enterprise deal. | Vaibs + Glenn + Mark | 30-min internal strategy call needed (Mark, Vaibs, Nick, Kriti, Kathy, Glenn) on 2027 Anthropic relationship aspiration. Last deal walked away at $11M — need a new angle.
3 | Claude licenses for all 57 attendees | Procure Claude access ahead of the event. | Vaibs / IT | Check Anthropic team pricing. Blocker for Day 2 afternoon hands-on.
4 | Replit vs Claude time split | Confirmed: Replit ~1hr morning, Claude rest of day. But need final call on whether Replit is introduced at Monday dinner (pre-work via QR) or in-session. | Vaibs / Adi | Mark's preference: Monday dinner QR → people arrive warm Tuesday morning.
5 | App / exercise to build | Which app does each group build on Day 2 afternoon in Claude? Tied to per-function pre-briefs. | Vaibs / Nick / Adi | Pre-briefs already drafted for all 11 groups — need domain lead sign-off (e.g. Laura for HR) before sending out.
6 | Group composition sign-off | 11 groups of 5 with tech leads — Mark to review and approve composition. | Mark Moffat | Draft in 'Group Membership' tab. Vaibs/Adi have done the cut; Mark reviewing offline.
7 | Founder engagement — who and when | Which 6–9 founders across the 3 evenings/mornings? Confirm pitch: 10 min mic + stay for dinner. | Mark + Vaibs + Nick | Targets include Tessl, Traycer, 8090, Clay, Apollo, 11x, 6sense, Demandbase, Mutiny, Aisera, Glean. Tesla likely not worth it. 8090 demo tomorrow.
8 | Goldman — Joe Porter confirmation | Lock the Day 3 opening slot. | Mark Moffat (Eva prepping email) | Confirmed as direction; formal yes pending.
9 | NexGen KPIs — final framing | What makes the final KPI list on Day 3? Candidates: token consumption leaderboard, weekly active AI use, rev/employee, rev/R&D person, speed of product, adaptability. | Mark + Adi | Leaderboard caveat: Vaibs/Nick flagged that heavy token use ≠ productivity long-term (lines-of-code analogy). OK as short-term measure. Need the live leaderboard data pulled before the event.
10 | 1x factory visit | Keep on Day 3 afternoon, move to Day 4 optional, or drop? | TBD | Currently slotted Wed 15:45–16:30 but tight. Leaning toward Day 4 optional.
11 | Day 3 afternoon structure | Group playbacks only, or playbacks + Andreas + factory? Sequencing TBC. | Mark + Adi | Current draft: playbacks → Andreas → factory (optional) → closing.
12 | Tool decision for hands-on | Replit confirmed for morning. Tessl / Traycer / Cursor — in or out? | Vaibs Kumar - 90-10 Done | John P checking availability on Tessl and Traycer.
13 | Wi-Fi / AV capacity | Confirm venue can handle 57 concurrent heavy users + screens/mics/power. | Eva / Venue | High priority — blocks Day 2 entirely if not resolved.
14 | Local admin rights on machines | IT to confirm all attendees can install/run Replit + Claude tools. | Robi / Jorge (IT) - Adi/Vaibs
15 | Dinner venues (Mon/Tue/Wed) | Three venues — or repeat? Mon + Wed at hotel, Tue offsite currently. | Eva
16 | Hotel block + airport transfers | Lock Stanford Park Hotel rooms and SFO/SJC transfers. | Eva / Kate | Collect attendee flight details.
17 | Pre-read / pre-briefs distribution | When do the 11 function pre-briefs get sent out? Who signs off each? | Adi / Vaibs | Domain leads (e.g. Laura for HR) to review within 24h, iterate, then send to groups.